## Tally Integration
S No | Task Name | Task Description | Start Date | End Date | Task Status | Developer
1 | Export Data | i. Get XML Data from Tally, ii. Load Request iii.Save Request iv. Process Response | Feb/16/2016 | Feb/19/2016 | In Progress | Daniel
2 | Processing Tags | i. Prcoess Tags to Type of Data ii. Match Data to Type of Data iii.Query Existing Data from Engine to Update | Feb/22/2016 | Feb/26/2016 | Not Started | Daniel
3 | Back Up Existing Database | Saving Database file to another location everytime before the changes are going to be made, with time and date and filenaming | Feb/29/2016 | March/04/2016 | Not Started | Daniel
4 | Sync of Data | i.From Tally, ii. To Odoo Engine iii.From Odoo Engin iv. To Tally | March/07/2016 | March/11/2016 | Not Started | Daniel
5 | Update / Upgrade | i. Get Data ii. Validate or Process iii. Update Database | March/14/2016 | March/18/2016 | Not Started | Daniel